## Slide 1: Brazosport ISD
Citizens’ Bond Oversight Committee
June 18, 2014

## Slide 2: Welcome
Introductions
  Staff
  Committee Members
  Others

## Slide 3: Charter
Reminder of Committee Purpose
In the interest of time and others, schedule separate meetings to discuss other topics.

## Slide 4: Website Review
www.brazosportisd.net
Comments or Recommendations

## Slide 5: Minutes
Comments, Questions or Changes to the Minutes???
Motion to approve the minutes...

## Slide 6: Project Status
  May 31, 2014 – Total P.O.’s issued – $21,035,587 or 51.73% completed or in progress. Actually paid $15,618,257
  February 28, 2014 – Total P.O.’s issued – $16,985,919 or 41.77% completed or in progress. Actually paid $14,390,951

## Slide 7: Review of Timelines
Project Timelines – See Website
www.brazosportisd.net

## Slide 8: Spring/Summer Projects
Student computer lab replacements - Ordered
Classroom Projection/Whiteboard – In progress
Roofs – Polk, B’Wood (Partial), B’port (Partial), Gyms at Clute and LJI
HVAC’s (LLC, Roberts)
Security Fencing – almost complete
Playgrounds – Equipment in District – scheduling installation
Culinary Lab – Late Summer/Early Fall
Welding and Agricultural Upgrades – Planning Stage
CN Serving Lines – Scheduled for install 1st week of August.
Security Vestibules – installation begin September 2014
Bus Parking
Others…

## Slide 9: Re-allocation
Three reallocations…
  Keyless Entrances –
    5/1/14 - $6,354 – Reporting only
    5/30/14 - $24,791 – Reporting only
    6/18/14 - $100,000 – Requesting approval to expand # of doors.
  Pull from “Wired Infrastructure” line item
Motion to approve the re-allocation above.

## Slide 10: Questions/Discussion/Suggestions
Meeting Schedule
  Sept 17, 2014
  Dec 17, 2014
  Begin at 5 pm.